Working with Support from ChildFund International

P.O.BOX 737, Gulu, Uganda; Email: acholicfpfedn@gmail.com

# ANNUAL REPORT FY2020-2021 JULY 2020-JUNE 2021FY

JUNE 2020

Table of Contents

COVER PAGE

2020	1

CONTENTS	2

ACRONYMS	2

MESSAGES FROM PROGRAM MANAGER	4

EXECUTIVE SUMMARY	5

INTRODUCTION	6

ABOUT ACFP	6

SUMMARY ACCOUNTABILITY PEFORMANCE	8

A) BUDGET VARIANCE ANALYSIS	8

B) SUMARY OF PARTICIPANTS SERVED	8

PROGRAM ACHIEVEMENTS	9

PO 1: Caregiver Empowerment Initiatives	9

SI 1.1: Promote IGA, Saving and Credit Access	9

PO 2: Entrepreneurship and Business Development Initiatives	9

PO 3: Early Childhood Development (ECD	10

SI 3.1: Strengthen Pre-school Quality Learning	10

PO 4: Child Protection	11

SI 4.1: Strengthen Community Based Child Protection (CBCP) System	11

SI 4.2: Strengthen Linkage between Child Protection Actors and Community	11

SI 4.3: Promote Child Protection Behaviour Change	11

PO 5: Community Health Initiatives	11

SI 5.1: Improve Water Access, Hygiene and Sanitation (WASH)	11

SI 5.2: Strengthen Family Healthcare Practices	12

SI 5.3.0: Improve Healthcare Utilization	12

PO 7: Youth-Livelihood, Sexual Reproductive Health and life skills	13

SI 7.1: Support Youth Vocational and Business Skills Development	13

SI 7.2: Promote Sexual Reproductive Health	13

PO 8: Youth Engagement in Community Decision, leadership	14

GRANTS AND NON-SPONSORSHIP PROJECT	15

Alert Management	15

CHILD SPONOSORSHIP	15

Sponsor Retention Rate	16

Disaster Risk Reduction	17

INTERNAL CAPACITY BUILDING	17

Staff and Structures Capacity	17

MONITORING AND EVLUATION	18

PARTNERSHIP	19

FUND PORTFOLIO	21

Annex 1: Detailed those children who were supported for further medical and Education attention	22

ACRONYMS

ASP                             Area Strategic Plan

AOP                            Area Operating Plan

ACFP			Acholi Child and Family Programme

ANC			Anti Natal Care

ASRH			Adolescent Sexual Reproductive Health

CYEC			Children Youth Executive Committee

CVS 			Child Verification Status

DFC			Designated Funds Certificate

ECCD			Early Childhood Care and Development

ECD			Early Childhood Development

EID			Early Infant Diagnosis

DCDO			District Community Development Officer

FAB			Farming As a Business

GPA			General Parents Assembly

ECP			Empowering Communities to Protect children

HIV			Human Immune Virus

MCH			Maternal Child Health

NSP			Non Sponsorship Funds

PDD			Project Design Document

PEC			Parents Executive Committee

PMTCT		Prevention of Mother to Child Transmission

PNC 			Post Natal Care

RTIs			Respiratory Tract Infections.

SRH			Sexual and Reproductive Health

STI 			Sexually Transmitted Infections

VHT			Village Health Team

VSLA			Village Savings and Loans Association

EMTCT		Elimination of Mother to Child Transmission of HIV

CBCPM                     Community Based Child Protection Mechanisms

VAC                           Violence Against Children

GBV                           Gender Based Violence

MESSAGE FROM PROGRAM MANAGER

Acholi Child and Family Programme (ACFP) is grateful for the smooth working relation with ChildFund which has enabled ACFP to impact on the lives of the children, youth and community members. In this financial year 2020/2021, program implementation continued to be hampered by the Covid-19 pandemic restrictions. ACFP realized slight decline in the projected funds partly as a result of the covid-19 pandemic which has affected the entire globe. Through funding and support from ChildFund, ACFP successfully implemented sponsorship and program activities including capacity building interventions using funds from subsidy, grants and local contribution. Through this program interventions, ACFP reached 7,659 children, youth and caregivers in the four supported communities.

With funding received, ACFP successfully implemented most of the planned activities save for a few activities in quarter four whose implementation was interrupted by the inter district lockdown restrictions Activities not implemented will be replanned in the coming FY2021/22.

Further, i want to commend Country office for sharing the PBF reports and the technical support which we have been able to receive this FY. We look forward for continued good working relationships

EXECUTIVE SUMMARY

This report presents the various activities that were planned and implemented by ACFP  in the financial year 2020/2021. It also presents achievements recorded.

Broad Achievements

Cumulative burn rate overall in programs is at 92%, Implying that most of the outputs are being delivered to program participants.  The above burn rate resonates with the overall programs participants reached at 7659 both enrolled and non-enrolled participants. These figures shows that ACFP Has steadily continued to reach out to the vulnerable communities within her Areas of operation for the Fiscal year 2020/2021.

Livelihoods projects especially agriculture is the backbone and traditional, cultural and social fibre in Acholi region. We continue to empower family groups to perform their roles through implementing the well-designed economic empowerment initiatives at household levels with support from government line departments aimed at improving food security and improved household income using various livelihood initiatives.

Child protection is being the core programs ACFP implements to reduce child abuse, ACFP has invested a lot of synergies on Child protection support structures through continues capacity building, Support in case management through working with different stakeholders. ACFP has now zeroed her efforts in using the already invigorated community structures like VHTs, CPCs and police to address their plight of children at risk of abuse and those affected by abuse and violence.

FY21 saw a shift in the education system amplified by the outbreak of Covid-19, this has negatively affected the normal functionality and progress of education across the region for over a year now, in abide to support home learning, a lot of resources were committed in supply of reading materials to over 4,600 children in the districts of Gulu, Agago and Kitgum. This was done in preparation of phased opening of schools.

Overall ACFP with support from various stakeholders has directly targeted enrolled families with programs such as medical screening, IGA support to 52 groups,supported10 caregiver groups with planting materials in Patongo and Ibakara, installed borehole in Punena for community use, supported child protection initiatives using community support structures, supported community initiatives to stop the  spread Covid-19 through spot messages and use of VHTs household to household sensitizations as well as supplying of hand washing facilities to the 8 supported schools among others.

ACFP has attributed all the FY21 achievement to continuous support from Child Fund Uganda, contribution of Various stakeholders, Partners and parents and children within her areas of operation. We believe that this FY22 with add a significant achievement in our overall Areas strategic plan, vision, Mission and goals working with vulnerable communities in Acholi Sub-Region.

INTRODUCTION

ABOUT ACFP

Acholi Child and Family Programme (ACFP) is a child centred NGO registered with Uganda National NGO-Board. The organization works with support from ChildFund International and is an umbrella organization of four community affiliate CBOs (Punena & Laroo Child and Family Programme (Gulu district) Ibakara Child and Family Programme (Kitgum district) and Patongo Child and Family Programme (Agago district). With regard to statistics from UBOS (2015), the organization’s operational areas (Gulu, Kitgum and Agago) have an estimated total population of 1,083,973 (Male=534,584 and Female=549,389).

From the AOP 2020/2021, three (3) Project Design Documents (PDDs) were developed to be implemented in this Fiscal Year. ACFP program interventions are hitched on life stages programing i.e. life stage 1 (Healthy and Secure Infants), Life stage 2 (Basic Education) and Life stage 3 (Youth Empowerment/Livelihoods). Further to the regular subsidy programs. This report is therefore a presentation of the activities implemented during FY 2020/2021 with highlights on key achievements, outcomes and challenges encountered during the period.

|  | Name of Community Projects | Ibakara, Patongo, Punena and Laroo child and family program |
| --- | --- | --- |
|  | Sub Region of Operation | Acholi sub region |
|  | Districts of Coverage | Gulu, Kitgum, Agago and Omoro districts |
|  | Number of Sub-Counties of Coverage | 9 (Bungatira, Unyama, Laroo Division, Koro, Kitgum-Matidi, Lagoro, Patongo TC, Lukole, Patongo) |
|  | Number of parishes of coverage | 235 |
|  | Number of villages coverage | 349 |
|  | Number of Staff | 25 (03 Child Fund staff, 22 ACFP staff) |
|  | Project Manager | Julius Ronald Wepondi |
|  | Contact | Julius Ronald Wepondi, Program Manager ACFP, Tel: 0774060684/0704552238, Email: wepondi@gmail.com |
|  | ACFP Address | Acholi Child and Family Program P.O.BOX 737, Gulu, Uganda Email: acholicfpfedn@gmail.com |

CORE INTENT

ACFP aims to empower communities whose children, youth and caregivers make lasting improvement in their lives to realize a bright future. This will be done through establishing a self-sustaining community which provide holistic development for the children and youth to become responsible young adults who care and protect the children in their societies.

SUMMARY ACCOUNTABILITY PEFORMANCE

A) BUDGET VARIANCE ANALYSIS (UGSH ‘000) A) BUDGET VARIANCE ANALYSIS (UGSH ‘000)

| Life Stages | Annual Budget Current FY (A) | Cumulative Annual Expenditure To date (B) | Burn Rate on Annual Budget (E) E=B/A*100% | Total Budget Current Quarter (C) | Total Expenditure Current Quarter (D) | Burn Rate on current Quarter Budget (F) E=D/C*100% |
| --- | --- | --- | --- | --- | --- | --- |
| Life Stage 1 | 91,097,992 | 91,682,000 | 100.6% | 20,991,040 | 5,710,500 | 27% |
| Life Stage 2 | 221,371,230 | 111,337,997 | 50% | 46,010,322 | 29,795,900 | 65% |
| Life Stage 3 | 58,451,954 | 820,800,385 | 1,404% | 49,700,951 | 33,729,364 | 68% |
| Capacity Building | 180,920,000 | 123,787,100 | 68% | 57,165,931 | 52,054,600 | 91% |
| Sponsorship | 90,363,600 | 70,814,610 | 78% | 27,773,500 | 26,041,000 | 93% |
| Community Contribution | 8,640,000 | 00 | 00 |  |  |  |
| Total | 650,844,776 | 1,218,422,092 |  | 201,641,744 | 113,602,000 |  |

Sources: Finance BVA and M&E reports,

B) SUMARY OF PARTICIPANTS SERVED

|  | Adults | Girls |  |  | Boys |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Age Group | 25 or older | 0-5 years | 6-14 years | 15-24 years | 0-5 years | 6-14 years | 15-24 years | Total Counts |
| Grants / NSPs / Emergencies | 75 | 24 | 3 |  | 26 | 3 |  | 131 |
| Community wide; (Both non- enrolled and enrolled families / children) | 140 |  | 165 | 110 | 53 | 250 | 69 | 787 |
| Enrolled Children |  | 300 | 712 | 169 | 267 | 743 | 222 | 2413 |
| Siblings of Enrolled Children |  | 615 |  |  | 1182 |  |  | 1,797 |
| Parents / Guardians / Caregivers of enrolled children | 2390 |  |  |  |  |  |  | 2390 |
| Government staff / structures | 71 |  |  |  |  |  |  | 71 |
| Partner Affiliate Staff and structures | 70 |  |  |  |  |  |  | 70 |
| Sub Total by Gender and Life Stage | 2746 | 324 | 1495 | 279 | 346 | 2178 | 291 | 7659 |

Sources: Activity enrollment card and Coverage table

# PROGRAM ACHIEVEMENTS

PO 1: Caregiver Empowerment Initiatives

Outcome 1.0: Increased % of children 0-5 living in economically growing and resilient households

### SI 1.1: Promote IGA, Saving and Credit Access.

ACFP conducted household vulnerability assessment to 913 (Males 481, Females 432). enrolled families in Patongo and Ibakara communities during the reporting period. The assessment aimed at ascertaining the level of household livelihoods vulnerability in the face of COVID-19 pandemic. Other areas that were also assessed included emerging child protection issues, Sexual reproductive health, general health and nutrition of enrolled children. The target participants included both children and caregivers. The results were used to target household in different interventions in livelihood, child protection and other income generating activities. A total of 913 households of enrolled families were assessed

A total of 52 groups belonging to the households assessed were trained in various enterprises and supported to start businesses for daily incomes. These businesses are supporting in provision of children’s needs like health, education and food.

SI 1.2: Promote Positive Parenting

ACFP conducted 4 parenting reflection and dialogue meetings for child protection with duty bearers and stakeholders on minimum standards of safe home environment, GBV prevention and positive parenting in the financial year in Laroo, Punena, Ibakara and Patongo. The dialogue helped the duty bearers to identify protection issues affecting children and youth and the mitigation measures to prevent and respond to the identified child protection issues. The dialogues that reached a total number of 142 (58 males, 84 females).

These sessions were done by VHTs with technical support from Probation office. The facilitators were supported with current parenting policy manual on topical issues of, who is a child, care for children, Role of parents in wellbeing of children and bottlenecks in parenting in communities among others.

During the training the facilitator noted that much of the parenting issues have been on child welfare and education which the parents blame on limited source of daily income for the households.

During the joint program monitoring a number of caregivers had remarked that many parents now days spend quality time with their children. “My father used to come home late in the night, he could hardly buy food for us, but after the training he has changed much of his time he spends with us “said Lakica 12 year old enrolled child in Patongo community

## PO 2: Entrepreneurship and Business Development Initiatives.

ACFP planned trained 40 TOTs in micro enterprise development. The trained TOTs rolled down was planned to enable households acquire knowledge and skills in enterprise development so as to support boost their livelihoods security and resilience which would in turn increase the capacity of providing quality and timely educational, health, shelter, nutritional and parenting needs to children with in the community.

40 participants trained in the 04 communities; In Punena 10 people were reached (03 females, 07 males) of whom 09 were from enrolled families. In Laroo, 13 participants were reached (11 females, 02 male) 11 of whom were enrolled parents.

In Ibakara 10 (08 males ,02 females) and 08 of them were enrolled parents., in Patongo,7 participants were trained (3Males and 4).

The trained TOTs rolled down the trainings in various family groups across all the four communities of Laroo, Punena, Ibakara and Patongo. 5 caregiver groups were trained in the four communities on Micro Enterprise Development Initiative (MEDI) a total of 472 (F=241, M=231). The training was to enable the group members acquire knowledge and skills to improve on their livelihoods security so that growth and development of infants and young children in their homes is improved. This training was facilitated by the district agricultural officer, commercial officer and the community development officer respectively.

By the end of the training, participants were well equipped with knowledge and skills in business development. During a sponsorship education session, a number of beneficiaries testified that the intervention had improved caregivers’ saving culture, access to financial services and business ideas for example some groups have managed to buy plastic chairs, plates and saucepans out of their saving to help each other during social gathering

Following the training of  caregiver groups across all the communities on Micro Enterprise Development Initiative, ACFP through support from District Production Departments in Gulu, Agago and Kitgum Provided extension services to caregivers’/youth farmers via extension workers. The purpose was to provide on-site knowledge on management of different farmer enterprises trained in that is poultry, piggery, crop production and income generating activities of selling and buying of produce the progress of the various enterprise and also to provide on-site/technical assistance on enterprise management. 1369 (449 males, 920 females) caregivers and youth acquired skills in record keeping, collective marketing and general enterprise management through extension services.

There is much improvement in record keeping, market access and collective efforts in enterprise management as well as sharing of successes amongst groups.

During monitoring Many family groups across the four communities of Punena, Ibakara, Patongo and Laroo were able to provide records of beneficiaries, various progress reports and individual income generating activities shared by the extension officers

Recommendation

- There is need train more caregiver groups and seed capital given for various businesses.

- The family groups need to be supported to register at sub-counties and trained on how to compete fairly for government projects such as NUSAF and may others.

Recommendations that were raised by the extension worker;

- There need for increased frequency of extension services to curb the spread of pest and disease that may arise in the due course.

- Regular follow up of the caregivers in their groups to backstopped them in the areas of weakness.

SI 2.2: Strengthen Agri-livelihood

(Training in Agri-livelihood, farming as business, Agric-production inputs, Agric-IGA management, post-harvest handling, etc.).

ACFP in partnership with District agri-Departments in Kitgum and Agago Districts trained caregivers and youth groups on farming as a business in Patongo and Ibakara communities.

The training enabled caregivers acquire knowledge and skills in farming as a business so that it would support boost their livelihoods security and resilience which would in turn increase the capacity of providing quality and timely educational, health, shelter, nutritional and parenting needs to children with in the community. The target participants included both caregivers and youth

The participants are from the 10 family groups, 5 in Patongo and 5 in Ibakara.By the end of the training, participants were well equipped with knowledge and skills in Farming as a business. The groups trained were supported with farm agro inputs of their choice.

The caregivers were from Patongo and Ibakara communities, Inputs ranged from groundnuts, maize-longe5. 526 (245 males,281 females) caregivers and youth received seeds.

The participants are from the 10 family groups, 5 in Patongo have a maximum of 30 caregiver and youth each group.

271 were from Ibakara and 255 caregivers were from Patongo. Currently only 6 out of the groups supported planted the seeds and the 4 groups did not plant because of weather pattern with hope of planting in the second season.

The planted crops are doing well and there is hope for a good harvest in the month September.

PO 3: Early Childhood Development (ECD)

Outcome 3.0: Increased % of children 3-5 years attending organized pre-school learning opportunities.

### SI 3.1: Strengthen Pre-school Quality Learning

ACFP Trained 23(12M,11Female) ECD center management committees and caregivers, on child centered learning and assessment methods. The activity that was  quarterly took place in only  two communities of Ibakara and Punena. The activity for Punena was facilitated by the CCT of Gulu coordinating centre while Ibakara and Patongo were facilitated by CCT Kitgum Coordinating center. For Ibakara, it was conducted at community office. This activity was intended to create awareness on ECD management, child centered learning and first aid. The intention here was that the management committee and the caregivers are refreshed on their roles and responsibilities.

ACFP renovation of 01 ECD centre at Ibakara. The renovation is part of the efforts to provide safe and friendly learning environment for the children enrolled at the ECD, ACFP also constructed the three stance latrine at Unyam ECD in Laroo. However, roll down on the training of centre management committees and caregivers could not continue since government closed and stopped operation of Early Childhood Centres across the country due to Covid-19 outbreak.

Outcome 4.0: % reduction in cases of violence against children in supported Communities

## PO 4: Child Protection

### SI 4.1: Strengthen Community Based Child Protection (CBCP) System

ACFP with partnership with probation and welfare offices in Gulu, Kitgum and Agago planned and conducted three child protection coordination meetings in the communities of Laroo, Punena, Ibakara and Patongo. The meetings comprised of LC1 chairpersons, CPCs, Police and Health workers and was planned with the aim of strengthening VAC case management at Sub County, Parish and Village level as a result of increased cases of violence against children in the face of Covid-19 pandemic.

Actions that were previously set were reflected on and resources re-assessed. The different duty bearers were assigned tasks and timeline set for when specific tasks needed to be completed. In the last meeting, a rapid mapping of child protection systems identifying formal / less formal structures “mechanisms” had been conducted and a referral pathway developed.

Initially the pathways were only distributed at sub-county level. Due to need for referral pathways at parish and village level, copies were made by the sub-county and given to LC1 chairperson ad CPCs.

The referral pathways were replicated and disseminated to the duty bearers at parish and village level during the meeting with all the contacts, services provided and location of the different duty bearers.

of reaching Total of 77 (45males, 32 females) CPCs across four communities of Laroo, Punena, Ibakara and Patongo Participated in the meetings. This has improved on cases reporting and management across all the communities.

### SI 4.2: Strengthen Linkage between Child Protection Actors and Community

ACFP support 57 child survivors and victims of violence / abuse to access justice in Gulu, Kitgum and Agago during the reporting period. The interventions on Violence against children are aimed at establishing linkages with services providers for victims of abuse/ violence and children with special needs and at risk of abuse.

In the current reporting financial year cases of Neglect topped the list of common abuses, school dropout and Early marriages across the three districts where ACFP operates.

In addition to provision of services and direct support to victims of child abuse, ACFP embarked on the awareness drivers in communities on need to protect children through community engagements and sensitizations.

Overall of the reported cases 25 were on child neglect related to health and welfare,28 were on child dropout at school and 4 were on early marriage and girls been affected much compared to boys. However, in event of case management there has been gaps in psychosocial and Financial support to victims and survivors in the process of justice which has been amplified by corruption in institutions of mandate.

57 (Female 32, Male 15) cases of violence against children (i.e. Defilement, child neglect, GBV, torture, were reported and supported by the organization in the reporting period. From the cases reported through the different CBCPMs, child neglect is still high in the four Communities. The community case management system has been re-strengthened in partnership with other CSO, Police, CPCs and CDOs, through the sensitizations, communities are now able to report and identify cases of VAC in the communities for support.

| Community | Nature of case | Action taken |
| --- | --- | --- |
| Patongo | Child neglect – 10 cases | Supported the police to conduct a family dialogues with their parents, relatives and clan heads |
|  | GBV – 4 cases | Family mediation Was transported to police. Spouse was remanded |
|  | Defilement – 1 case | Police was facilitated to arrest the perpetrator. |
| Punena | Early Marriages – 3 Cases | Facilitated police to conduct arrest |
|  | Child neglect – 7 cases | Facilitated police to locate the immediate families and reunite with the children. |
| Laroo | Torture (physically abused ) – 1 cases | Facilitated police to transport the girl from Gulu back to Omoro district |
|  | Drop out– 24 case | Facilitated police to arrest perpetrator. |
| Ibakara | Child neglect – 8 cases | Supported CDO to conduct and family dialogues and reunite the children with immediate family members |

### SI 4.3: Promote Child Protection Behaviour Change.

ACFP Printed and Distributed 924 posters and IEC materials in the 04 communities of Patongo, Ibakara, Punena and Laroo. VHTs, CPCs and LC1 secretaries for children and women’s affairs were also given copies of the posters to use as illustrations during community sensitizations on handwashing best practices, parenting and learning

ACFP together with Community services departments in Gulu, Agago and Kitgum conducted 3 radio talk shows to sensitize masses of Covid-19 prevention and Child protection issues that were reported amidst the Lockdown i.e. child abuse and neglect, school dropouts among others.

ACFP trained teachers and parents, and youths on child CFA, child protection, child participation/VAC in all the four communities: Laroo, Punena, Ibakara and Patongo. This was to empower Children to hold their parents and duty bearers accountable on the decision making process and also to put in consideration children and youth issues on the development agenda at village to district level, 129 (64 males, 65 females) participants trained.

ACFP supported initiatives on parents, and youths on child Friendly accountability, child protection, child participation, celebration of day of African child as well as media advocacy campaigns on child protection this was done across the four communities: Laroo, Punena, Ibakara and Patongo. This was to empower Children to hold their parents and duty bearers accountable in decision making and aspect of child involvement in matters that affect them 152 children participated in advocacy through media across the supported communities, Children and youth were able to participated in the National celebrations like day of African child, Women’s day among others and children and youth issues were presented at various floras.

As a result, Children are empowered to demand for their rights from various stakeholders and duty bearers. A case in point was in Ibakara during Child fund media tour, two children were identified to present issues they feel need to be addressed by the president “we wish that the government of Uganda provides all children with home reading materials during this lock down” said Brenda one of the child advocate in Ibakara.

03 awareness sessions on the legal framework in schools and communities were conducted in Patongo 30 (Male 17, Female 13, Enrolled 15), Laroo 82 (Male 45, Female 37, enrolled 27) and Punena 45 (Male 24, Female 21). Of the participants reached life stage two children were 120 and the rest were adults. Participants were able to recognize there constitutional mandate in protection of child from abuses and any form of exploitation and the existing institutions to enforce such mandates.

Children, Youths and adults were in engaged in identifying gaps in child protection service delivery within their communities as indicated below. The different communities conducted the activity with children/ youth in and out of school and parents. CDO, OC CID, teachers and CFPU police office took lead in guiding the discussions in the different communities.

Below are some of the concerns that the different categories were presented.

| Children | Youth | Adult |
| --- | --- | --- |
| - Limited dissemination of legal instruments. - Children’s issues not given priority by institutions of government . - children are not given time to participate in advocacy for their rights | - Youth are not consulted in issues that affect them. - Cases youth are one sided they tend to favor female sex - Youth innovations not supported. | - Community believe that Child Protection actors are only the police and the LC 1s - Corruption is so high among the actors - There is a lot of un healthy beaucracy in handling child protection cases at community and higher institutions of government. |

PO 5: Community Health Initiatives

SI 5.1: Improve Water Access, Hygiene and Sanitation (WASH)

ACFP in partnership with sub-county health assistants formed, Trained and functionalize school WASH committees in the eight supported schools of Pageya, Gulu PTC, Lokodi, St. Martine, Kitgum Matidi, Layamo, Patongo and Moodege primary schools, the aim is to promote hygiene and good sanitation in schools. This targeted children and senior women/men teachers in the supported schools. 75 were trained (46 males, 29 females)

ACFP with partnership with District water department of Gulu district trained water user committee in Punena community on safe water chain management. This was done to equip the water user committee with knowledge and skills on maintaining the water and safe water chain components in the community. The training was done by the district water officer Gulu district in partnership with health assistant of Bungatira sub-county. A total of 9 members were trained 5males and 4 Females.

ACFP in the month of June drilled a community borehole at Punena community. This borehole is benefiting approximately 250 households within community and support the community ECD access the clean water for domestic use, reduction on water related diseases at community and improved hygiene and sanitation at household level.

ACFP procured and supported 8 community schools with hand washing facilities in the bid to improve hygiene and sanitation at schools and prevent the spread of Covid-19. The items purchased were footstep handwashing facilities, water collecting item, Sanitary towels for girls and detergents among other. Communities are accessing clean and safe water for domestic use, hygiene and sanitation practices have improved, reduction of cases of water related diseases reported during the first month of water usage, Community sensitizations on WASH done during assemblies and proper maintenance of sanitation facilities has improved on hygiene and sanitation levels at home and schools as this was reported during joint program monitoring by district technical teams in quarter four program quality reflection meetings.

SI 5.4: Stopping transmission of COVID-19 to families and communities

ACFP procured and distributed 106 megaphones to 67 VHT’s attached to 06 health center; Laroo, Unyama, Punena, Kitgum-Matidi, Akuna-laber and Patongo. Further, 39 PEC members also received the megaphones to support in disseminating COVID-19 information to the enrolled families. Each VHT and PEC member received 02 pairs of dry cells to use in the megaphones. The megaphones procured to ensure that VHTs safely delivered health education outreaches on stopping transmission of COVID-19 to families and communities. As part of promoting implementation of the COVID-19 SOPs put in place by Government, the organization also provided 67 face masks and 67 bottles of sanitizers to the VHTs for use during community engagements, the VHTs conducted weekly health education outreaches in the communities where ACFP project beneficiaries live and approximately 2000 households were reached. The VHT were facilitated with monthly incentives by ACFP.

Information around handwashing best practices, COVID-19 signs and symptoms as directed by WHO and good health seeking practices, increasingly communities have adopted the COVID-19 preventative measures as directed by Government in the Ministry of Health SOPs. Families have hand washing facilities in place at their homes and medical services are sought promptly

Outcome 5.0: Reduced cases of childhood illness/ injury / malnutrition

## PO 5: Community Health Initiatives

ACFP with Partnership with District Health department through HCIIIs conducted medical screening camps across all the four community offices of Patongo, Ibakara, Laroo and Punena.

This exercise involved screening of children on common killer diseases like malaria, skin infection, Deworming and Malnutrition among others.

The children identified to be sick were given treatment and critical cases referred for further management in respective District hospitals.

Critical issues identified.

215 children were diagnosed of malaria, 122 tape warms and skin infections as this is as a result of early rains that have facilitated breeding of mosquitos and use of dirty water sources within communities, a total of 1205 (627M, 578F) Children were medical examined and supported with first line treatment for various cases identified.

Parents of life stage 1&2 were sensitized on management of Childhood illnesses and management of cases and reporting, as a result parents are now able to report such illnesses to the hospital for support.

### SI 5.3.0: Improve Healthcare Utilization

In partnership with health sub district teams, ACFP conducted 3 integrated health outreaches in Patongo, Punena, Ibakara and Laroo communities. Children under five and pregnant mothers were reached with knowledge on early disease identification and management. During outreaches, the services provided included immunization, testing and treating of common illnesses, nutritional messages, ANC, FP and HCT. 2,213 (F 1112, M 1101. Enrolled 300) adults were tested for HIV were 213,Life stage one 72, Life stage two 179) children were screened and treated/immunised of common childhood illnesses. 22 children were diagnosed with malaria and treated. 88- life stage one children were reached with nutritional assessment and counselling services. 132  mothers were reached with ANC services while 144 were sensitized  on modern family planning methods.

Outcome 6.0: Increased % of children meeting grade appropriate minimum level of literacy and numeracy

PO 6: Child Friendly Learning Environments

SI 6.1: School Health and Safe School Infrastructure

SI 6.3: Literacy and numeracy development

In a bid to continue providing access to learning for children in Acholi with the evolving education modalities; i.e. over the radio learning, tele-education, different online platforms such as zoom, skype, google and provision of self-leaning materials, ACFP printed and distributed learning materials to 4,602 children in the 04 communities. The organization targeted enrolled children with their siblings to help them continue self-learning from home.

A total of 4,602 children benefited enrolled and siblings, below is a break down per community. Beneficiaries; Life stage. Gender. Community/CBO; Male; Female; LSI; LSII; LSIII. Ibakara; 438; 372; 450; 471. Patongo; 498; 384; 855; 54. Punena; 724; 835; 1383; 123. Laroo; 623; 728; 1023; 181. 2283; 2319; 3773; 829. Total.

As a result, children are motivated to read while at home since each child of school going age in the family was provided with learning materials. Several parents have also testified that the materials have enabled children take interest in referring back to their school notes during self-learning time and some have taken interest to call on air learning programs to seek understanding on areas that they found challenging.

ACFP conducted 04 awareness campaigns on child education across four communities. Create awareness on inclusive participation towards child education and also role of various stakeholders in child’s academic achievements at school level. Total of 864 (M416 448F) parents were sensitized across all the four communities of Laroo, Punena, Ibakara and Patongo this was done in collaboration with CCTs and Education departments in the three districts of Gulu, Kitgum and Agago. This targeted caregivers of school age going children.

ACFP facilitated CCTs and District school inspectors to conduct three support supervision and monitoring of the 8 supported school Gulu PTC, Lokodi, St. Martine, Kitgum Matidi, Layamo, Patongo and Moodege primary schools.

ACFP facilitated CCTs and District school inspectors to conduct three support supervision and monitoring of the 8 supported school Gulu PTC, Lokodi, St. Martine, Kitgum Matidi, Layamo, Patongo and Moodege primary schools.

ACFP as well conducted education forum in four communities of Laroo, Punena and Patongo. The purpose to discuss and come up with improvement plans to betters learner’s performance. This was done in partnership with respective education departments in Gulu, Agago and Kitgum, this activity involved various education stakeholders like parents, PTA, SMCs, opinion leaders and political and local leaders at district and community level, action plans were developed by each school in improvement of school performance, resource mobilization and other governance related issues on welfare among others, The schools have all adopted feeding program in order to improve of school retentions level, Formation and functionalization of Readers and writers clubs across the Eight supported schools.

ACFP in partnership with education department and CCT supported to conduct 3 oral language, competition and competence initiatives. In the Eight supported schools of Gulu PTC, Lokodi, St. Martine, Kitgum Matidi, Layamo, Patongo and Moodege primary schools. The main purpose of the initiative is to improve on literacy and Numeracy levels, subject competencies and improve on the reading culture among learners. Total of 932(475M 457F) learners participated in the initiative across the supported schools.

As a result of all the above interventions, Parents attitude towards education of both boys and girls has changed positively this was reported in the number of girls who sat for the primary leaving exams increased from 46% in 2019 to 53 in 2020 and 2021 respectively. this was reported during termly education forums in Kitgum and Agago respectively.

There improvement in the life skills of children, comprehensive and reading skills both indoor and outdoor school activities

SI 6.4: Capacity development for teachers and caregivers.

ACFP in partnership with education departments trained teachers in the supported schools of Gulu PTC, Lokodi, St. Martine, Kitgum Matidi, Layamo, Patongo and Moodege primary schools on setting assessments. This is aimed at enhancement of teacher’s capacities to develop and set assessments based on subject competences as this will in turn improve on children’s performance in class and ensure effective teaching and learning. A total of 54 (28M,26F) teachers were trained.

Teachers are able to develop and moderate class level learner’s assessments and this is improving of learning out comes on various competence per subject across all the supported schools a report shared by CCTs during Joint inspections and Program monitoring in the supported schools.

PO 7: Youth-Livelihood, Sexual Reproductive Health and life skills

Outcome 7.0: % youth employed in safe jobs (non-exploitative) earning a living wage meeting their basic needs

### SI 7.1: Support Youth Vocational and Business Skills Development.

The project Provided counselling and guidance to youth on career choices related to non-exploitative work. This was to prepare out of school youths (boys and girls) for gainful non- exploitative employment (formal/self). Youth comprise of the biggest population in our)

A total of 25 youths were identified with support from PEC/CYEC and staff to be supported acquire vocational skills training. The aim was to empower enrolled youth who are out of school with vocational skills of their choices so that they can be self-reliant individuals.

Following the reopening of institutions to finalists by government of Uganda, the 25 youths under vocational skilling program at Kitgum Technical Institute resumed school. The youth had earlier been selected from the 3 communities of Patongo 7, Punena 9 and Laroo 9.

Ibakara through the Household Resilience Project supported 50 youth for the program.

Since the youth had just Completed school in the month of June, ACFP could not procure for them start up tools as was planned. The tools will be procured in FY22. However, all the youth are currently attached for internship in various private workshops within their communities for hand on experience in the trade of training.

### SI 7.2: Promote Sexual Reproductive Health

PO 8: Youth Engagement in Community Decision, leadership

Outcome 8.0: % of youth with strong positive adult, peer relations and actively engaged in civic events

In a bid to increase youths’ social skills and create platforms where they can learn and share information around Sexual Reproductive Health, ACFP Formed and functionalized 4 virtual spaces and peer groups for to ease the roll down of youth related interventions. Youths from Ibakara, Punena, Laroo and Patongo were targeted with the activity.

A total of 28 (09 females, 19 males) youth group leaders participated in forming virtual platforms to better engage and share information with other youths. Each community there after formed a youth what sup group to which they added medical personal, Agricultural extension workers, the probation and welfare officers of their different districts, CFPU OCs, teachers and local role models. A question for discussion is posted weekly around sexual reproductive health, non-exploitative work, human rights etc. and the youth share their understanding on the issue with guidance from a technical person.

As part of creating a platform for youth to voice their opinions, share information and influence decisions, Four Voice Now groups were mapped and formed in each of the ACFP communities. With support from field staff these youth groups will be able to engage meaningfully in them.

A total of 45 (08 females, 37 males) youth group leaders participated in forming virtual platforms to better engage and share information with other youths. In the quarter topics that the youth have discussed have been around civic education, how they can practice their fundamental right to elect a leader in a peaceful manner, how they as leaders can encourage fellow youth to prevent COVID-19 infection through promoting the government SOPs.

The platform has enabled youths to address myths around COVID-19 i.e. if you take alcohol you cannot be infected by COVID-19. these myths were cleared with support from health workers that were invited on the planform to have health chats with the youth, the platforms have enabled youths to socialize with peers and share health and career concerns with technical persons. The discussions have kept youth engaged during their stay at home which has limited them from falling prey to negative peer influence.

ACFP supported children and youth agency in youth adult partnerships and conducted 04 youth adult partnerships sessions across four communities of Laroo, Punena, Ibakara and Patongo. The purpose was to promote equal participation and decision making among the youth and adults. The sessions were facilitated by the Community Facilitators and staffs from respective communities. 151 (85M, 66F) participated, through this engagements youth have advocated for youth friendly corners and youth spaces for life skills and development.

SI 9.2 Basic Accountability Performance

(……...explain the table below in this space)

| Accountability indicators | FY21 Target (A) | FY21 Achievement FY (B) |
| --- | --- | --- |
| - % of enrolled children present | 100% | 100% |
| - % of enrolled children who Participated in program | 100% | 66% |
| - % of enrolled children attending ECD | 100% | 20% |
| - % of enrolled children attending basic education: | 100% | 100% |
| - % of enrolled children with met health needs | 5% | 1% |

SI 9.3 Alert Management

ACFP supported 27 child alert cases (14 Males, 13 Females) during the Financial Year across all communities. Of the alerts 23 were health related.  ACFP supported in clearing the medical bills and 4 related to rehabilitation of burnt houses, CFP supported in the procurement of building materials for the construction of the shelters that burnt and collapsed and finally 2 were education related ACFP supported the two clear the school fees balances enabling the two children to sit for their final examinations.

ACFP registered 5 deaths in the Financial year across communities. 4 were health related and one child accident drowning. ACFP provided psychosocial support to the families.

SI 9.4 Sponsor Retention Rate (includes all other activities of sponsorship)

Child Focused Event

ACFP conducted Child focused events across all the four communities. Children took part in a number of child related activities like letter writing, dance competition, poems among others. This was aimed at building the skills of children as they engage with one another. A total of 2012(963M, 1049F) children were reached and participated in the event.

File Assessment

ACFP conducted File assessment exercises across the four communities with support from Programme Officer-Sponsorship. This was aimed checking our levels of compliance in as far as documentation of valuable documents are concerned. We found great improvement in regards to filing carbon copies of letters across the four communities. Documentation of DFC above 30 dollars improved, staff are making good use of file access book. We recommended community staff to open files for the newly enrolled children whose files were yet not in place.

DFC monitoring

ACFP conducted DFC monitoring exercise across the four communities with support from Programme Officer-Sponsorship. This was aimed at checking our levels of compliance in as far DFC management is concerned. We found great improvement in regards to documentation of DFC above 30 dollars.  Management of items bought by children’s DFCs has greatly improved among parents/caregivers.  Children and caregivers give positive impacting stories DFC is creating in their lives. 357(186M, 171F) children who had received DFCs were monitored. L1= 120, LS2 197 and LS3 40.

Child Processed Reports processed.

ACFP processed 2209(955 males, 1254 females) Child processed reports for both sponsored and non-sponsored children. A total of 1770 child progress reports were sent out to the sponsors in different countries.  1233 were sent to alliance countries and 467 to USA, and 68 to Korean.  This is in abide to promote sponsor retention and acquisition.

Conducted Sponsorship community education.

ACFP conducted sponsorship education in all the four communities. This was done in family groups and at zonal level. A total of 1617 (754M, 863F) participants were reached. Participants were educated on the sponsorship procedures among them were child enrolment, departures, alerts response, DFCs utilization and management of DFC items, correspondence timelines and turn round. Beneficiaries’ expectations were cleared and the organization expectations of parents made clear to the beneficiaries.

Conducted monthly and quarterly family home visits.

ACFP with support from Parents Executive Committees and staff conducted family visitation in all the four communities reaching to 2214 (M=1101, F=1113) enrolled families of these LS1 were 489, LS2 1410 and LS3 315. During these visits they were able to share with families what we do as office, shared with them also topics related to GBV, child protection, IGAs and others. They were also able to get used to the newly developed reporting tools designed to capture all valuable information regarding family visitation.

Orientation and validation of service providers and local volunteers on child safeguarding

Service providers and volunteers (PEC) were oriented on the child protection and safeguarding policy. This was done at community where PECs and service providers especially for meals were mobilized to community offices and oriented on child safeguarding.  This was done to ensure that we the people we deal with are well versed with the issues around child protection and are of reputable character when it comes to child safeguarding and protection.  This was done in all the four communities. The volunteers and service provider signed the children safeguarding/ protection policy as their commitment to ensure children are safe and free from violence. A total of 79(49M, 30F) volunteers and services providers were oriented.

Train staff and volunteers on child identification, family visitations / content collection.

ACFP trained 67(44 males, 21 females) staff and volunteers on child identification, family visitations and content collection across the communities. The Sponsorship Programme officer facilitated the training. This was done to empower structures and staff to carry out meaningful family visitations and identification of the right beneficiaries for enrollment and program targeting.

06 (4males, 2 females) Staff were as well trained on photography and quality narrative development. This was in abide to build staff capacity to ensure sponsor acquisition and acquisition and retention. Country office staff took lead in the training.

Procurement of SR Stationery

ACFP procured office assorted stationery for four communities of Laroo, Ibakara, Punena and Patongo to facilitate sponsorship and program work both at community and area office level for the whole Financial Year.

Internal Capacity Building

Staff and Structures Capacity

Staff training on quality correspondence management

ACFP trained community staff across all communities on writing quality correspondence management. We shared quality tools like the correspondence tracking tool, family visitation tool and quality narrative formats. The target was the CDFs and CDAs. 8 (6 Males, 2Females) community staff were trained.

PM trained A/O team on documentation and filing. The training focused on the key focus areas while filing. A total of 6 staff (3 males and 3Females) were trained in filing and documentation.

Staff Quarterly Meetings

ACFP conducted four staff quarterly meetings. These meetings were aimed at assessing staff performances in the quarters as well as share with the staff strategies for reach out to beneficiaries and come up with the modalities. Among other discussion were on team building, adhering to reporting and accountabilities timelines, closing of the financial year and adherence, completion of CPRS among others. In attendance were the CDFs, CDAs, security guards, area office staff and the Board chairperson 22 (17M, 5F) attended the meetings.

Board Meetings

ACFP conducted 3 quarter meetings for the board executives. The meetings discussed the strategies for implementing during the COVID period approved budget and work plan for the F/Y 2021. Staff key results areas among others. In total 4 board members (03M,01F) female attended the meeting with the SMT.

Facilitated quarterly PEC/CYEC Meeting

ACFP facilitated PEC/CYEC meetings in the four communities. Leading issues discussed were implementation of activities, improving on family visitation, monitoring of programs and strengthening family groups. 83 (56M, 27F) PEC/CYEC attended the meetings in communities of Laroo, Patongo, Punena and Ibakara.

Facilitated Parents’ General Assemblies

ACFP supported four communities of Laroo, Punena, Ibakara and Patongo to conduct general Parents Assembly. This is to present FY21 accountabilities for the various intervention during the financial year, also to generate ideas for the new FY22 planning which to be developed. A total of 978 (470M, 508F) parents participated in the meetings across all the communities.

Operational Capital Investment

ACFP procured two lap-tops in the quarter. One for the Sponsorship Program Officer and Accounts Assistant. This will support in efficient service delivery in the two departments

ACFP installed solar in Patongo community, the space will be used as office space for Patongo office. Area office was renovated as well.

ACFP installed lightening arrester in the A/O. This will protect the office promises and staff from lightening.

ACFP procured 6 office chairs for community staff 04 CDF and 2 for the Programme officers.

4 Nikon 3500 were purchased for community offices to facilitate Programme and sponsorship work.

SI 9.5 Disaster Risk Reduction

Risk Management

ACFP constructed 03 grass thatched houses for 03 families that were affected by water logging and flooding after river Agago burst its banks during rainy season. This year, the region received a lot of rainfall as compared to the previous year and several families were affected by water logging that destroyed crops and housing among other things. The 03 families who had settled near the river bank were most affected and lost their and homes in the process. The constructions are underway pending final finishes.

Program Portfolio Review and Development:

ACFP conducted 4 quarterly Program quality review meetings across the communities. The review meetings aimed at sharing with key stakeholders’ activities implemented within the quarters, Quality of designed projects, challenges encountered and recommendations. It attracted key stakeholders like head teachers, health in chargers, key sub-county officials, parent’s executive committee representatives and children and youth. They were fruitful engagement with the structures; they were able to understand activities we do in their respective communities however were very much concerned about strategies we use to mobilise participants and implementation since Covid-19 has affected certain activities in terms of numbers. A total 73(49M, 23F) participants were reached.

Monitoring and evaluation

Monitoring and evaluation is considered one of the most important of programing aspects that inform on the progress, Modality of program implementation, impacts to the beneficiaries among others. ACFP with support from Country Office M/E department conducted a three days training in M/E basics. The training attracted only the CDFs and Area Office staff. Areas presented were Child verification Monitoring (M&E level 1&2), reporting, data analysis and interpretation, CDF reporting tools, the dashboard, quality success stories and photos taking. We believe to experience lots of change especially on the quality of our report, emphasis was put on building the capacity of staff in M&E level 1 &2. A total of 8 (M=6, F=2) members participated.

In the bid to achieve the core program out comes, ACFP conducted 3 integrated Program monitoring with the district technical wings in the four community offices with a sole purpose of improving on the program implementation, ensuring that programs reach the targeted beneficiaries and also draw lessons for program quality improvement among others. During the monitoring cases of un reported alerts were identified and limited engagement of family groups in program delivery.

Recommendations

All program implementation must be done at family group level.

Re-organization and strengthening of family groups across all the communities.

Carry out sponsorship education to educate caregivers on our sponsorship processes.

Innovation

Partnership.

FY 21 ACFP partnered with the following department in program implementation.

- Child Fund Uganda

- District Education departments

- District Health Departments

- District Production departments

- District Agri departments

- Community service departments

- And local leaders, CSOs etc.

Key challenges

- Low turn up of participants due to COVID-19 restrictions

- Slow pace in activity implementation especially community wide and education related since education sector is not yet fully opened.

Lessons learnt

- Involvement of stakeholders at district and sub-county level has improved on program delivery models and quality program implementation.

- Implementation through family groups has enhanced program participation

Action plans

- Consistent monitoring of DFC and programs to impact on the livelihoods of the beneficiaries.

- Need to sensitize caregivers on the alert management during sponsorship education

- Family group is the implementation niche and all family group data must be updated with current enrolled Families.

- All activities involving stakeholders must be implemented prior to sharing of TORs with respective heads of departments and implementing staff.

FUND PORTFOLIO

| FY FUNDING TYPE | EXPENDITURE (USD; 000) |
| --- | --- |
| Grants | 46,597,770 |
| Sponsorship | 26,041,000 |
| Non- Sponsorship Funding | 168,000 |
| Community Contribution | 00 |

| DIRECT EXPENSE BY CORE PROGRAM AREA | EXPENDITURE (USD; 000) |
| --- | --- |
| Livelihood /Micro Enterprise Development Initiatives | 106,376,471.52 |
| Early Childhood Development | 104,376,471.52 |
| Child Protection | 301,376,471.52 |
| Health (Nutrition) | 127,399,579.52 |
| Basic Education | 155,894,745.52 |
| Sexual Reproductive Health and Life Skills | 111,376,471.52 |
| Youth Engagement in Community Decision, leadership | 210,181,669.52 |
| Emergency | 2,184,000 |

| DIRECT EXPENSE BY DISTRICT | EXPENDITURE (USD; 000) |
| --- | --- |
| e.g. |  |
| Gulu | 300,000,000 |
| Kitgum Agago | 516,981,881 302,184,000 |

Life Stage 1 focuses on children 0-5 years and their caregivers, siblings

Life Stage 2 focuses on children 6-14 years and their caregivers, siblings

Life Stage 3 focuses on youths 15-24 years of age, caregivers, siblings